## Sheet1
Working Plan
Period
Domain | Module | Tasks | Assigned to | Date to begin | Date to finish | Days | Description
Acquirer | Merchant Online Store | Web App + repport | Lahcen | 2020-04-15 | 2020-04-25 | 10
|  | Mobile App + repport | Nasreddine | 2020-04-15 | 2020-04-25 | 10
|  | MPI (Merchant Plug-In) + repport | Lahcen | 2020-04-26 | 2020-04-30 | 5
|  | Payment Gateway + repport | Nasreddine | 2020-04-26 | 2020-04-30 | 5
|  | VM of issuer domain + VPN | Lahcen
|  | VMs: interoperability and acquirer domains + VPN | Nasreddine
Issuer | Cardholder | Card + Account + ... ? + repport | Lahcen | 2020-05-01 | 2020-05-05 | 5
|  | ACS(Access Control Server) + repport | Lahcen | 2020-05-01 | 2020-05-05 | 5
Interoperability |  | DS(Visa Directory Server) + repport | Nasreddine | 2020-05-06 | 2020-05-10 | 5
|  | Authentication History Server + repport | Nasreddine | 2020-05-06 | 2020-05-10 | 5
| 3D Secure implimentation | ???